## Sheet1
Freedom Bugs (Blockers)					Notes	Unverified
Bug #	6.0 (Present?)	Fixed Upstream	Fixed Version #	Fixed in Ubuntu/Debian Version	Corresponding Trisquel Version
6733	Yes	No	N/A	N/A	N/A
6248	Yes	N/A	N/A	N/A	N/A
6007	Yes	No	N/A	N/A	N/A
5995	No	Yes	Not in 6.0	Quantal	6.5
5994	Yes	No	N/A	N/A	N/A
5984	No	Yes	1.5	Precise	6.0
5981	Yes	Yes	1.17.dfsg-1	Raring	7.0
5957	Yes	No
5956	Yes	Reported	N/A	N/A	N/A	Upstream appears to be considering package removal
5954	Yes	Possibly	N/A	N/A	N/A	Was this mailing list post ever followed up on?
5953	Yes	No
5950	Yes	No
5830	Yes	Reported
5807	Yes	Partially				Solution seems simple, remove both packages. Both have non-free dependencies
5806	Yes	Reported	N/A	N/A	N/A	Upstream appears to be attempting to re-license	X
5805	Yes	Reported	N/A	N/A	N/A	Upstream appears to be attempting to re-license	X
5518	Yes	Reported					X
5426	Yes	Partially	0.8.64+dfsg-1 (Licensing) / Non-free recommendation not fixed	Raring	7.0	This bug has 2 separate issues. Firstly, the license of the e-book included in the package. Secondly, the ebook recommends non-free software. The licensing issue has been fixed upstream. The recommendation has not.	X
5374	Yes	No					X
5102	Yes	Reported				Upstream appears unlikely to fix. Package helper written, see bug report.	X
5017	Yes	Reported					X
4570	Yes	Reported	N/A	N/A	N/A		X
4237	Yes	Yes		Quantal (Backports)	6.5		X
3843					X
3842	Yes	Yes	23.4+1-1	Quantal	6.5		X
2338					X
1942	Yes	No	N/A	N/A	N/A	Package helper written, see bug report.	X
1364	Yes	Yes	2011.20120322-1	Quantal	6.5		X
1350	Yes	No				Unable to test with my hardware, Presumed to be present in 6.0	X

Minor Quick Fixes	Type
5007	Grammar